## Sheet1
Step | Deadline | Date range |  |  | Comments
Grant due at the NIH | Grant submission deadline | 2025-02-05 |  |  | Edit the date and then the other dates will calculate
Grant due at research administration | 1 week prior to Grant submission deadline | 2025-01-29 |  |  | Research adminstration might give some leeway, but best to plan for one week
Suggested time to reach out to Dr Ceglia to inform possible mock study section | 3 to 4 months in advance of the grant submission deadline | 2024-10-16 | to | 2024-11-13 | Earlier ok too!
|  | Latest time for mock study |  | Longer time prior to mock study
|  | (5 weeks prior to submission deadline) |  | (8 week prior to submuission example shown here)
Mock study section | 5 to 8 weeks prior to Grant submission deadline | 2025-01-01 | to | 2024-12-11 | The greater time prior to submission, the more time to revise given comments
Submission of materials to reviewers for mock study section | 2 weeks prior to mock study section | 2024-12-18 | to | 2024-11-27
Latest time to request mock study by submitting completed intake form | 4 weeks prior to mock study section | 2024-12-04 | to | 2024-11-13 | Please note that mock study sections can take several weeks to identify reviewers so more time is appreciated to enable us to find the best review group for you.
Optimal time to request mock study by submitting completed intake form | 8 weeks prior to mock study section | 2024-11-06 | to | 2024-10-16
Formulas:
Date range = [Date range, row above]-7
Date range = [Date range, row above]-2*7